University of Prince Mugrin - College of Business and Tourism

International Hospitality Management

Course: HMGT 327 – Fundamentals of Project Management

Facilitator: Dr. Elhussein Ibrahim

Assignment No: 1 – Infographic: Project Stakeholder Management

Student’s Name: [Write your full name]

Student’s ID No.: [Write your ID]

Section No.: [Write your section]

Date of submission: Saturday, 3 October 2026

Project Stakeholder Management

1. Definition of Project Stakeholder and Stakeholder Management

A project stakeholder is any individual, group, or organization that may affect, be affected by, or perceive itself to be affected by a decision, activity, or outcome of a project (Project Management Institute [PMI], 2021). Stakeholders can be internal, such as the sponsor, the project team, and senior managers. They can also be external, such as customers, suppliers, investors, government bodies, and the local community (Freeman, 1984).

Stakeholder management is the set of processes used to identify these people, analyze their expectations and their influence on the project, and develop strategies that engage them effectively in project decisions and execution (PMI, 2017).

2. The Project Stakeholder Management Plan

The stakeholder management plan is part of the overall project management plan. It is built through four steps (PMI, 2017):

• Identify stakeholders: list everyone involved in a stakeholder register with their role, interest, and influence.

• Plan stakeholder engagement: analyze each stakeholder’s power and interest, compare their current and desired engagement levels (unaware, resistant, neutral, supportive, leading), and choose strategies.

• Manage stakeholder engagement: communicate, meet their needs, resolve issues, and build support.

• Monitor stakeholder engagement: track relationships and update the plan as the project changes.

The plan usually contains:

• the stakeholder register

• the power and interest analysis

• the engagement levels

• the communication requirements (what, how, how often, and by whom)

• the engagement strategies

• who updates the plan and when it is reviewed

3. Why Is Stakeholder Management Important?

• Wins support: secures commitment, approvals, and resources from key people.

• Reduces risk: spots resistance and conflict early, before they delay the project.

• Aligns expectations: agrees on scope, quality, and success criteria, which limits scope creep (Larson & Gray, 2021).

• Improves decisions: uses stakeholders’ knowledge and feedback.

• Builds trust: clear and regular communication protects the organization’s reputation.

• Increases project success: satisfied stakeholders are more likely to accept the final deliverables (Bourne, 2009).

4. Stakeholder Management Strategies

A common tool is the Power/Interest Grid (Mendelow, 1991):

• Manage closely (high power, high interest): involve them fully and make decisions together. Examples: sponsor, owners, key clients.

• Keep satisfied (high power, low interest): meet their needs and consult them on key decisions without overloading them. Examples: regulators, senior executives.

• Keep informed (low power, high interest): send regular updates and listen to their concerns. Examples: staff, end users, community.

• Monitor (low power, low interest): watch for changes and keep communication light. Example: the general public.

Engagement can also be seen as a spectrum: Inform → Consult → Involve → Collaborate → Empower. The project manager increases a stakeholder’s involvement as their power and interest grow (PMI, 2021; Kerzner, 2022).

5. Stakeholder Management in the Hospitality Business

Hospitality projects include opening a new hotel, renovating rooms, introducing a new booking system, or organizing a large event. Each group of stakeholders gets a different strategy:

• Owners and investors (manage closely): they approve budgets and expect a return, so they receive regular progress and cost reports.

• Government and regulators (keep satisfied): the Ministry of Tourism, the municipality, and civil defense must approve licenses and safety standards.

• Employees (involve): staff are trained on new systems and services because they deliver the guest experience.

• Suppliers and contractors (collaborate): the hotel agrees contracts, delivery dates, and quality standards with them.

• Guests (keep informed): guests are told about noise or closed facilities, offered alternatives, and asked for feedback.

• Community, online travel agencies, and tour operators (keep informed): keeping them informed protects the hotel’s reputation and its booking channels.

Example: A hotel near the Prophet’s Mosque in Al-Madinah plans a renovation. The project manager:

• holds monthly meetings with the owners

• gets Ministry of Tourism approvals early

• schedules the work outside the peak Umrah and Ramadan seasons

• gives guests and Umrah tour operators advance notice

• trains front-line staff before reopening

As a result, guests are less disturbed, regulatory delays are avoided, and the project supports the tourism goals of Saudi Vision 2030.

References

Bourne, L. (2009). Stakeholder relationship management: A maturity model for organisational implementation. Gower.

Freeman, R. E. (1984). Strategic management: A stakeholder approach. Pitman.

Kerzner, H. (2022). Project management: A systems approach to planning, scheduling, and controlling (13th ed.). Wiley.

Larson, E. W., & Gray, C. F. (2021). Project management: The managerial process (8th ed.). McGraw-Hill Education.

Mendelow, A. (1991). Stakeholder mapping. In Proceedings of the 2nd International Conference on Information Systems. Cambridge, MA.

Project Management Institute. (2017). A guide to the project management body of knowledge (PMBOK guide) (6th ed.). Project Management Institute.

Project Management Institute. (2021). A guide to the project management body of knowledge (PMBOK guide) (7th ed.). Project Management Institute.